## December
Date | Days | Work title | Details | work status
15/12/2025 | Monday | BLOOD_BANK:Architecture | create the folder and create the 3-tire architecture of this project | Done
16/12/2025 | Tuesday | BLOOD_BANK:github | create the repository for this project and add the project in this repository | Done
|  | BLOOD_BANK:database | the postgreSQL database connect with this project | Done
17/12/2025 | Wednesday | BLOOD_BANK:Table create | create the all required table for this project which tables are users,donorsrecipients,inventory,donations,requests and matches | Done
18/12/2025 | Thrusday | BLOOD_BANK:Backend->AdminController | make the admin login with role and store token | Done
|  | BLOOD_BANK:Backend->authMiddleware | make the authMiddleware for the secure authentation | Done
|  | BLOOD_BANK:Backend->roleMiddleware | make roleMiddleware fro rolebase authentation and for access | Done
|  | BLOOD_BANK:Backend->adminRoutes | create the api of the admin login
19/12/2025 | Friday | BLOOD_BANK:Backend->POSTMAN | testing the api for admin login in postman | Done
|  | BLOOD_BANK:Backend->authController | build authController for backend.This file will contain all the logic for CRUD operations on users: list, view details, update, delete donors | Done
20/12/2025 | Saturday | BLOOD_BANK:Backend->authRoutes | build authRoutes for backend. This will contain CRUD routes list, view details, update, delete for users. | Done
|  | BLOOD_BANK:Backend->POSTMAN | Testing the api for getuser,getuserByID,updateUser and deleteUser | Done